## DevHours
Project
| Task | Start | End | Days
Priority Procedure Service
| Version 4 Windows Service | 2012-02-06 | 2012-03-09 | 25
| Syncronous Procedure Execution | 2012-03-12 | 2012-03-19 | 6
| Loading (and reload) from file system | 2012-03-20 | 2012-04-02 | 10
| Version 4 (XML) Client control | 2012-04-03 | 2012-04-24 | 16
| Oracle Support | 2012-07-18 | 2012-08-07 | 15
| Licence control Module | 2012-08-08 | 2012-08-14 | 5
Enterprise Data Appliance
| User Environment Object | 2012-04-25 | 2012-05-08 | 10
| User Provisioning Module | 2012-05-09 | 2012-05-22 | 10
| XML View Control | 2012-05-23 | 2012-06-19 | 20
| XML to ADO conversion | 2012-06-20 | 2012-07-17 | 20
| Label Printing | 2012-08-15 | 2012-09-13 | 22
Shop Floor Data Capture
| Production Reporting Module | 2012-09-24 | 2012-10-29 | 26
| 2d Imager support | 2012-10-30 | 2012-11-19 | 15
| Version 3 Client Interface | 2012-11-20 | 2012-12-03 | 10
| Label Printing | 2012-09-14 | 2012-09-21 | 6
| XML form designs stored on server | 2012-12-04 | 2012-12-10 | 5
Content Management
| Priority Ecommerce integration | 2012-01-02 | 2012-01-20 | 15
Royal Mail Integration
| SOAP based datasource for RMX integrations | 2012-01-23 | 2012-02-03 | 10